## MPR1
[16 empty] | Format-MPR1 | [12 empty] | Format-MPR1 | [13 empty] | Format-MPR1
Monthly Reporting Format for Physical and Financial Progress under PMGSY | [15 empty] | Sept, 2015
State: Uttarakhand |  |  |  | Progress upto 30 Sept, 15 | [5 empty] | (Length in km, Amount in Rs. Lakhs)
# | Phase | Clearance | [12 empty] | CumulativeAmount Released by MoRD | Funds Transferred from State | Total Available Fund | Progress During the Month-Sept, 15 | [12 empty] | Cummulative Progress
|  | New Connectivity | [6 empty] | Upgradation |  |  | Total | [5 empty] | New Connectivity |  |  | Habitations Connected |  |  |  | Upgradation |  |  | Total |  |  | New Connectivity |  |  | Habitations Connected |  |  |  |  | Upgradation |  |  | Total
|  | Nos. | Length | Value | Habitations to be connected |  |  |  | Nos. | Length | Value | Nos. | Length | Value |  |  |  | Works Completed | Length of Completed Road Works | Expenditure | 1000+ | 999-500 | 499-250 eligible | Total | Works Completed | Length of Completed Road Works | Expenditure | Works Completed | Length of Completed Road Works | Expenditure | Works Completed | Length of Completed Road Works | Expenditure | 1000+ | 999-500 | 499-250 eligible | <250 | Total | Works Completed | Length of Completed Road Works | Expenditure | Works Completed | Length of Completed Road Works | Expenditure
[5 empty] | 1000+ | 999-500 | 499-250 eligible | <250
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
1 | I | 6 | 24.2 | 716.08 | 1 | 3 | 2 | 1 | 62 | 274.76 | 5317.29 | 68 | 298.96 | 6033.37 | 6063 | 0 | 6063 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 6 | 24.2 | 660.88 | 1 | 3 | 2 | 1 | 7 | 62 | 274.76 | 5143.36 | 68 | 298.96 | 5804.24
2 | II | 95 | 465.98 | 13559.34 | 46 | 37 | 25 | 51 | 0 | 0 | 0 | 95 | 465.98 | 13559.34 | 14041 | 136 | 14177 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 95 | 471.19 | 14448.2 | 46 | 37 | 25 | 51 | 159 | 0 | 0 | 0 | 95 | 471.19 | 14448.2
3 | III | 46 | 394.18 | 5615.13 | 24 | 16 | 18 | 26 | 0 | 0 | 0 | 46 | 394.18 | 5615.13 | 5415 | 3779 | 9194 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 45 | 394.55 | 8943.77 | 24 | 16 | 18 | 26 | 84 | 0 | 0 | 0 | 45 | 394.55 | 8943.77
4 | IV | 63 | 560.88 | 9737.14 | 25 | 59 | 49 | 56 | 16 | 29.25 | 687.86 | 79 | 590.13 | 10425 | 9853 | 2317 | 12170 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 63 | 560.64 | 11772.81 | 25 | 59 | 49 | 56 | 189 | 16 | 29.25 | 674.36 | 79 | 589.89 | 12447.17
5 | V | 101 | 888.31 | 20320.15 | 14 | 98 | 55 | 98 | 0 | 0 | 0 | 101 | 888.31 | 20320.15 | 20028 | 2968 | 22996 |  |  | 8.96 |  |  |  | 0 |  |  |  | 0 | 0 | 8.96 | 91 | 870.83 | 22365.8 | 14 | 96 | 51 | 88 | 249 | 0 | 0 | 0 | 91 | 870.83 | 22365.8
6 | VI | 88 | 727.81 | 21992.26 | 3 | 89 | 57 | 11 | 0 | 0 | 0 | 88 | 727.81 | 21992.26 | 19770 | 2597 | 22367 |  | 0.5 | 60.89 |  |  |  | 0 |  |  |  | 0 | 0.5 | 60.89 | 75 | 678.85 | 21587.42 | 3 | 86 | 43 | 7 | 139 | 0 | 0 | 0 | 75 | 678.85 | 21587.42
7 | VII | 117 | 1051.03 | 36331.77 | 0 | 96 | 60 | 2 | 0 | 0 | 0 | 117 | 1051.03 | 36331.77 | 20960 | 25 | 20985 | 1 | 5.45 | 70.39 |  |  |  | 0 |  |  |  | 1 | 5.45 | 70.39 | 72 | 896.85 | 25703.35 | 0 | 84 | 37 | 0 | 121 | 0 | 0 | 0 | 72 | 896.85 | 25703.35
8 | VIII | 101 | 711.4 | 24538 | 0 | 31 | 42 | 12 | 0 | 0 | 0 | 101 | 711.4 | 24538 | 15522 | 8 | 15530 | 1 | 0.5 |  |  |  |  | 0 |  |  |  | 1 | 0.5 | 0 | 64 | 643.34 | 18170.86 | 0 | 25 | 17 | 5 | 47 | 0 | 0 | 0 | 64 | 643.34 | 18170.86
9 | IX (RRP-II) | 29 | 34.74 | 4412.76 | 1 | 5 | 2 | 0 | 0 | 0 | 0 | 29 | 34.74 | 4412.76 | 3532 | 230 | 3762 | 1 |  | 19.99 |  |  |  | 0 |  |  |  | 1 | 0 | 19.99 | 7 | 27.7 | 2591.69 | 1 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 7 | 27.7 | 2591.69
10 | X (RRP-II) | 125 | 1132.75 | 46793.82 | 0 | 7 | 17 | 13 | 1 | 7.03 | 342.23 | 126 | 1139.78 | 47136.05 | 34819 | 0 | 34819 | 3 | 9 | 222.11 |  |  |  | 0 | 1 |  |  | 4 | 9 | 222.11 | 59 | 817.87 | 33981.72 | 0 | 5 | 11 | 1 | 17 | 1 | 7.03 | 283.85 | 60 | 824.9 | 34265.57
11 | XI (RRP-II) | 109 | 674.85 | 33554.75 | 2 | 11 | 26 | 8 | 0 | 0 | 0 | 109 | 674.85 | 33554.75 | 16974.6 | 552 | 17526.6 | 7 | 6.4 | 119.96 |  |  |  | 0 |  |  |  | 7 | 6.4 | 119.96 | 26 | 277.58 | 17057.38 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 26 | 277.58 | 17057.38
12 | XII (RRP-II) | 34 | 317.31 | 15100.25 | 0 | 1 | 9 | 8 | 0 | 0 | 0 | 34 | 317.31 | 15100.25 | 5993 | 76 | 6069 |  |  | 234.97 |  |  |  | 0 |  |  |  | 0 | 0 | 234.97 | 2 | 39.74 | 4470.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 39.74 | 4470.89
13 | XII (Reg. PMGSY) | 90 | 769 | 43289.93 | 2 | 15 | 139 | 74 | 42 | 535.62 | 18716.98 | 132 | 1304.62 | 62006.91 | 0 | 1328 | 1328 | [6 empty] | 0 | 1 | 2.65 | 680.28 | 1 | 2.65 | 680.28 | 0 | 126.12 | 6957.51 | 0 | 0 | 0 | 0 | 0 | 1 | 63.43 | 5222.77 | 1 | 189.55 | 12180.28
Total |  | 1004 | 7752.44 | 275961.38 | 118 | 468 | 501 | 360 | 121 | 846.66 | 25064.36 | 1125 | 8599.1 | 301025.74 | 172970.6 | 14016 | 186986.6 | 13 | 21.85 | 737.27 | 0 | 0 | 0 | 0 | 2 | 2.65 | 680.28 | 15 | 24.5 | 1417.55 | 605 | 5829.46 | 188712.28 | 114 | 413 | 256 | 235 | 1018 | 80 | 374.47 | 11324.34 | 685 | 6203.93 | 200036.62
Restoration* |  | - | - | - | - | - | - | - | - | - | - | - | - | - | 6161 | - | 6161 | - | - | 0 | - | - | - | - | - | - | - | - | - | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | 3721.72
Grand Total |  | 1004 | 7752.44 | 275961.38 | 118 | 468 | 501 | 360 | 121 | 846.66 | 25064.36 | 1125 | 8599.1 | 301025.74 | 179131.6 | 14016 | 193147.6 | 13 | 21.85 | 737.27 | 0 | 0 | 0 | 0 | 2 | 2.65 | 680.28 | 15 | 24.5 | 1417.55 | 605 | 5829.46 | 188712.28 | 114 | 413 | 256 | 235 | 1018 | 80 | 374.47 | 11324.34 | 685 | 6203.93 | 203758.34
* - Expenditure under Restoration have been included in total expenditure in various Phases (for ongoing works), hence seperate expenditure corrected accordingly.
Note : 1. Cumulative Expenditure included the State Share also. 2. In Col.-44 (length of completed road works), State is reporting partial completed length also but in ommas only the legth of completed roads is being displayed.